## Sheet1
Applications | Approved by app owner ? Yes/No | RFC approved? | Number of servers | RFC dates | Comments
CPAA - Non prod | Yes |  | 5 | 1st April
Big Data - Non prod |  |  | 50 |  | Just subscribe | hdp,edge,hnode,name,bd,infa,mgmt,rstudio
Ebiz - Non prod | Waiting for the response |  | 22
ERS - Non prod | Yes |  | 27 | 2nd April
Mulesoft | On Hold |  | 72 | On Hold | Work with Ganesh while patching
Online Bind | Yes |  | 9 | 2nd April
Anaconda Python | Yes |  | 6 |  | Just subscribe
DTEX | Yes |  | 7 | 13th April
Integris - Dev | Yes |  | 8 | 8th April
MRTS | Yes |  | 5 | 9th April
Splunk TX | Yes |  | 11 | 9th April
Splunk AO | Yes |  | 14 | 8th April
Bonitasoft |  |  | 7 |  | Just subscribe
Firm | On Hold |  | 31 | On Hold | Need to plan how to patch these servers
CPAA - Production | Yes |  | 5 | 13th April
SAN |  |  | 4 |  | Need to patch during working hours
Database | Yes |  | 1 | 14th April
ELK |  |  | 3 |  | Owner ??
Integris - Production | Yes |  | 8 | 16th April
Ebiz - Prod TX | Waiting for the response |  | 8
Big Data - Production |  |  | 76 |  | Just subscribe
MRM2 | On Hold |  | 25 | On Hold
Ebiz - Prod AO | Yes |  | 9 | 20th April
Ansible | Yes |  | 8 | 7th April
Guidewire | Yes |  | 4 | 20th April | Send msgs in morning - coordinate with Bryan Wilkinson, Carl Cole, and Bryan Faneuf for support and shakedown.
Satellite | Yes |  | 4 | 8th April
QueryGrid |  |  | 2 |  | Sent IM to Scott, waiting for the response to find out who is the owner
Pivotal Cloud Foundry | Yes |  | 4 | 21st April
Eschat/MySQL | Yes |  | 4 | 4th May | Create work order for DBA - no replication
Test | Yes |  | 13 | 9th April
Filenet | Yes |  | 12 | 14th April | Send msgs in morning - Work with Budda.Raj@aaa-calif.com & Dandikwar.Tirupati@aaa-calif.com
Lab | Yes |  | 1 | 9th April
NES | Yes |  | 3 | 9th April
ERS - Prod AO |  |  | 63 |  | Patch after the failover to TX
ERS - Prod TX | Yes |  | 61 | 23rd April
CLAS | Yes |  | 12 | 23rd April
Ebiz Lab | Yes |  | 2 | 23rd April
Redis | Yes |  | 3 | 21st & 23rd
SSIS | Yes |  | 1 | 23rd April
zTD-IBM | Yes |  | 2 | 23rd April
FileApp |  |  | 1
Unidentified |  |  | 10
AACG |  |  | 2
Total |  |  | 625